## Sheet1
Person | Week 5 | Week 6
Adam | 2 | 2
James | 4 | 5
Dax | 1 | 5
Mitch | 3 | 3
Sprint 3 Planning:
What we want to get done this sprint and how long will they take:
1 - Finish Log In Page – 1 Day.
2 - Finish User class and implement Currency – 2 Day.
3 - Make Order Class – 2 Day.
4 - Make Queue Page – 1 Day.
5 - Make Order Page – 2 Day.